## Activities
Activity Name | Type | Week | Responsible | Estimated Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1
Learn Eclipse | Preparation | 1 | Developer | 18 | 20 | Done | Learning SVN, Eclipse well critical to project success | -2 | 10
Role preferences | Coordination | 1 | Project Manager / Team Lead | 4 | 4 | Done | Quick meeting to align on roles | 0 | 0
Learn SVN | Preparation | 1 | Developer | 18 | 10 | Done | SVN server issues slowed progress | 8 | 80
Wiki setup | Preparation | 1 | Technical Writer / Developer | 12 | 8 | Done | Wiki structure set; content population ongoing | 4 | 50
Team formation | Preparation | 1 | Project Manager / Team Lead | 6 | 7 | Done | Finalizing team structure post-role preferences | -1 | 14.2857
Brainstorm project concept | Requirements | 1 | All Team Members | 8 | 8 | Done | Ideation session planned for project scope | 0 | 0
Project concept writeup | Documentation | 1 | Project Manager / Technical Writer | 6 | 6 | Done | To document brainstorming outcomes | 0 | 0
Identify role owners | Preparation | 1 | Team Lead / Project Manager | 4 | 5 | Done | Multiple roles are OK - think about role & reponsibility distribution | -1 | 20
Team Roster | Documentation | 1 | Project Manager / HR Coordinator | 4 | 6 | Done | Compiling team roles and contacts | -2 | 33.3333
Weekly team meeting | Coordination | 1 | Team Lead | 5 | 6 | Done | 1-hour kickoff meeting with all members | -1 | 16.6667
Weekly report | Documentation | 1 | Project Manager / Technical Writer | 3 | 3 | Done | Week 1 progress summary submitted | 0 | 0
Week 2
Repository setup | Preparation | 2 | Developer | 10 | 10 | Done | Configuring SVN for team access | 0 | 0
Define requirements | Requirements | 2 | Business Analyst / Team Lead | 16 | 17 | Done | Detailing functional and non-functional requirements | -1 | 5.8824
Create, share paper prototype | Requirements | 2 | UI/UX Designer / Frontend Developer | 12 | 15 | Done | Sketching UI prototype for feedback | -3 | 20
Requirements document | Requirements | 2 | Business Analyst / Technical Writer | 18 | 20 | Done | Formalizing requirements; needs team review | -2 | 10
Update activity tracker | Documentation | 2 | Scrum Master / Project Manager | 4 | 3 | Done | Logging Week 2 task progress | 1 | 33.3333
Create acceptance tests | Testing | 2 | QA Engineer / Tester | 10 | 10 | Done | Drafting tests for key requirements | 0 | 0
Choose processes | Coordination | 2 | Project Manager / Scrum Master | 6 | 5 | Done | Selecting Agile/Scrum for project | 1 | 20
Update risk/issues on Wiki | Coordination | 2 | Scrum Master / Project Manager | 4 | 4 | Done | Logging initial risks (e.g. | 0 | 0
Weekly team meeting | Coordination | 2 | Team Lead / Project Manager | 5 | 5 | Done | 1-hour status update meeting | 0 | 0
Weekly report | Documentation | 2 | Project Manager / Technical Writer | 3 | 5 | Done | Week 2 progress summary | -2 | 40
Week 3
System design | Design | 3 | System Architect / Senior Developer | 20 | 24 | Done | Creating architecture and data flow diagrams | -4 | 16.6667
Initial coding | Development | 3 | Developer / Software Engineer | 24 | 27 | Done | Starting core feature implementation | -3 | 11.1111
Unit testing | Testing | 3 | QA Engineer / Developer | 12 | 13 | Done | Writing unit tests for initial code | -1 | 7.6923
Code review | Review | 3 | Senior Developer / Team Lead | 8 | 7 | Done | Reviewing code for quality and standards | 1 | 14.2857
Update activity tracker | Documentation | 3 | Scrum Master / Project Manager | 4 | 3 | Done | Logging Week 3 task progress | 1 | 33.3333
Update risk/issues on Wiki | Coordination | 3 | Scrum Master / Project Manager | 4 | 4 | Done | Updating risks (e.g., coding delays) | 0 | 0
Weekly team meeting | Coordination | 3 | Team Lead / Project Manager | 5 | 4 | Done | 1-hour status update meeting | 1 | 25
Weekly report | Documentation | 3 | Project Manager / Technical Writer | 3 |  | Ongoing | Week 3 progress summary
Week 4
Feature development | Development | 4 | Developer | 28 |  | Ongoing | Implementing remaining features
Integration testing | Testing | 4 | QA Engineer | 16 |  | Planned | Testing feature interactions
Bug fixing | Development | 4 | Developer | 12 |  | Planned | Addressing issues from integration tests
Update documentation | Documentation | 4 | Technical Writer | 10 |  | Planned | Updating design and requirements docs
Update activity tracker | Documentation | 4 | Project Manager | 4 |  | Planned | Logging Week 4 task progress
Update risk/issues on Wiki | Coordination | 4 | Project Manager | 4 |  | Planned | Updating risks (e.g., testing delays)
Weekly team meeting | Coordination | 4 | Team Lead | 5 |  | Planned | 1-hour status update meeting
Weekly report | Documentation | 4 | Project Manager | 3 |  | Planned | Week 4 progress summary
Week 5
Final testing | Testing | 5 | QA Engineer | 20 |  | Planned | End-to-end system testing
Bug fixing | Development | 5 | Developer | 15 |  | Planned | Resolving final issues
Final documentation | Documentation | 5 | Technical Writer | 12 |  | Planned | Finalizing all project deliverables
Project presentation | Documentation | 5 | Team Lead | 10 |  | Planned | Preparing demo for stakeholders
Final delivery | Coordination | 5 | Project Manager | 8 |  | Planned | Submitting project deliverables
Update activity tracker | Documentation | 5 | Project Manager | 4 |  | Planned | Logging Week 5 task progress
Update risk/issues on Wiki | Coordination | 5 | Project Manager | 4 |  | Planned | Final risk and issue log
Weekly team meeting | Coordination | 5 | Team Lead | 5 |  | Planned | 1-hour wrap-up meeting
Weekly report | Documentation | 5 | Project Manager | 3 |  | Planned | Week 5 and project summary
Note on C1: swami: This is useful for generating subtotals and reports
Note on D1: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H1: swami: Insert your own comments
Note on I1: SE: This field is updated automatically

## Instructions
Using the activity plan
Fill in hours to be spent on each activity during each week
If 5 team members each will spend an hour, that counts as 5 hours
If you spend time on an activity not listed in the tracker, add the activity and list actual hours
For new activities, identify the type of activity - documentation, coordination, estimation etc.
Identify people responsible for each activity
Estimate the hours needed for the activity